## Sheet1
| Design | Redlining and Assets | HTML | Design QA
Project & Tasks
DTN
DTN Moodboard | Done | NR | NR | NR
Home Page | Done | NR | http://apttus.projecthost.us/htmls/files/2/DTN/HTMLCSS/20140811_042156/index.html | ETA - 7th Aug Resources ( Simple, Harsh)
Trading – Product Page | Done | NR | http://apttus.projecthost.us/htmls/files/2/DTN/HTMLCSS/20140808_080359/products.html# ETA - 6th Aug Resources - (Bobby, Satnam & Inder) | ETA - 6th Aug Resources ( Simple, Harsh)
Product Inner Page | Done |  | ETA - 7th Aug Resources - (Bobby, Satnam & Inder) | ETA - 7th Aug Resources ( Simple, Harsh)
View Cart | Done | NR | http://apttus.projecthost.us/htmls/files/2/DTN/HTMLCSS/20140808_080359/products.html# ETA - 7th Aug Resources - (Bobby, Satnam & Inder) | ETA -7th Aug Resources ( Simple, Harsh)
Compare Page | On Hold
Filter Page | On Hold
Configure Page | On Hold
My Account Page | 6th Aug Resource - (Rajeev Verma , Yogesh) | NR | ETA - 14th Resource - (Rajeev Verma & Yogesh) | ETA - 19th Aug Resources ( Simple, Harsh)
Orders Pages, History |  | NR
Subscriptions |  | NR
Subscription Renewal ETC |  | NR
Billing and Install address | Done | NR
Signup flow | Done | NR | http://apttus.projecthost.us/htmls/files/2/DTN/HTMLCSS/20140808_080359/signup.html ETA - 11th Aug Resources - (Bobby, Satnam & Inder) | ETA - 11th Aug Resources ( Simple, Harsh)
Click through version | Done | NR
Gap Analysis as per the reference document | ETA - 11th Aug Resources - (Rajeev Verma, Simple and Yogesh)
CPQ
Moodbord | Done | NR
CPQ Toollkit | ETA- Iteration on 6,7 and 8th Resources - Himmat Verma, Ajay | NR
Redisgn of Shopping Cart Exp | ETA- Iteration on 6,7 and 8th Resources - Himmat Verma, Nitesh
Installed Product Screens
Order Product Page | Done | NR | ETA - 14th Aug Resource - Baljinder, Inder | ETA - 19th Aug Resources ( Simple, Harsh)
Installed Product Page | ETA- Iteration on 4th Aug feedback - 5th Aug Resources - Rajeev Verma, Ajay | NR | "ETA - 12th Aug Resource - Baljinder, Inder | ETA - 14th Aug Resources ( Simple, Harsh)
Billing Metrics | ETA - Iterations on 8th, 11th and 12th. Resources - Rajeev Verma and Yogesh
Badger Templates
Moodboard
Initial Design Concepts
Aruba
Simplification of Quote Creation Process | Waiting on the access link to start